## CR-05 - Goals and Outcomes

Progress the jurisdiction has made in carrying out its strategic plan and its action plan.  91.520(a)

n Program Year 2024, the City of Long Branch successfully concluded its 5-Year Consolidated Plan period with significant accomplishments across all priority areas. The final year saw continued momentum in public service delivery, infrastructure improvements, and administrative efficiency, with most goals exceeding expectations.

Comparison of the proposed versus actual outcomes for each outcome measure submitted with the consolidated plan and explain, if applicable, why progress was not made toward meeting goals and objectives.  91.520(g)

Categories, priority levels, funding sources and amounts, outcomes/objectives, goal outcome indicators, units of measure, targets, actual outcomes/outputs, and percentage completed for each of the grantee’s program year goals.

| Goal | Category | Source / Amount | Indicator | Unit of Measure | Expected – Strategic Plan | Actual – Strategic Plan | Percent Complete | Expected – Program Year | Actual – Program Year | Percent Complete |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Administration | Administration | CDBG: $ | Other | Other | 1 | 1 | 100.00% | 1 | 1 | 100.00% |
| Improving Public Facilities | Homeless | CDBG: $ | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 97500 | 536259 | 550.01% | 12000 | 60805 | 506.71% |
| Infrastructure | Affordable Housing Public Housing | CDBG: $ | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 10000 | 188365 | 1,883.65% | 12000 | 30255 | 252.13% |
| Public Service | Non-Homeless Special Needs Non-Housing Community Development | CDBG: $ | Public Facility or Infrastructure Activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 0 | 54 |  | 0 | 54 |  |
| Public Service | Non-Homeless Special Needs Non-Housing Community Development | CDBG: $ | Public service activities other than Low/Moderate Income Housing Benefit | Persons Assisted | 5000 | 223765 | 4,475.30% | 1100 | 33272 | 3,024.73% |

Table 1 - Accomplishments – Program Year & Strategic Plan to Date

The Public Service category notably surpassed its targets, achieving over 3,000% of the one-year goal and nearly 4,500% of the 5-year goal. This reflects the city’s strong partnerships with local nonprofits and service providers, which expanded outreach and support for non-homeless special needs populations.

Infrastructure and Public Facilities investments also demonstrated exceptional performance. The city assisted over 60,000 individuals in 2024 alone through infrastructure projects, contributing to a cumulative total of over 536,000 persons assisted over the 5-year period. These improvements have enhanced accessibility, safety, and quality of life in low- and moderate-income neighborhoods.

The Administration goal remained consistent, with full completion of planned activities, ensuring effective oversight and compliance throughout the program cycle.

Overall, Long Branch exceeded its strategic goals in nearly every category. This success is attributed to strong inter-agency coordination, community engagement, and adaptive planning in response to evolving local needs. As the city transitions into a new Consolidated Plan period, these outcomes provide a strong foundation for future investments and policy development.

## CR-10 - Racial and Ethnic composition of families assisted

Describe the families assisted (including the racial and ethnic status of families assisted). 91.520(a)

|  | CDBG |
| --- | --- |
| White | 476 |
| Black or African American | 75 |
| Asian | 2 |
| American Indian or American Native | 0 |
| Native Hawaiian or Other Pacific Islander | 0 |

| Total | 553 |
| --- | --- |

| Hispanic | 435 |
| --- | --- |
| Not Hispanic | 241 |

Table 2 – Table of assistance to racial and ethnic populations by source of funds

In Program Year 2024, the City of Long Branch provided assistance to a total of 553 individuals through CDBG-funded activities. The racial and ethnic composition of those served reflects the city’s diverse population and its commitment to equitable service delivery.

These figures demonstrate that a significant portion of CDBG beneficiaries in 2024 were Hispanic, aligning with the demographic trends in Long Branch’s low- and moderate-income neighborhoods. The city continues to prioritize outreach and program accessibility for historically underserved racial and ethnic groups.

Over the 5-year Consolidated Plan period, Long Branch has consistently ensured that CDBG-funded programs are inclusive and responsive to the needs of its diverse community. The final year’s data reaffirms the city’s progress in reaching populations most in need, particularly within Hispanic and minority communities.

## CR-15 - Resources and Investments 91.520(a)

Identify the resources made available

| Source of Funds | Source | Resources Made Available | Amount Expended During Program Year |
| --- | --- | --- | --- |
| CDBG | public - federal | 457,589 | 238,479 |

Table 3 - Resources Made Available

During Program Year 2024, the City of Long Branch made strategic use of its federal Community Development Block Grant (CDBG) allocation to support priority activities identified in the Consolidated Plan. A total of $457,589 in CDBG resources were made available, of which $238,479 was expended during the program year.

These funds were directed toward public services, infrastructure improvements, and administrative functions, with a strong emphasis on serving low- and moderate-income residents. The city’s ability to effectively deploy these resources reflects its commitment to addressing community needs and maximizing the impact of federal investments.

As the final year of the 5-Year Consolidated Plan period, 2024 marked the culmination of sustained efforts to improve public facilities, expand access to services, and strengthen neighborhood infrastructure. The city’s use of CDBG funds has consistently aligned with its strategic goals, and the outcomes achieved this year reinforce the value of continued investment in equitable development.

Identify the geographic distribution and location of investments

| Target Area | Planned Percentage of Allocation | Actual Percentage of Allocation | Narrative Description |
| --- | --- | --- | --- |
| City-wide, emphasis on low/mod zones | 25 | 25 | Public Services |
| Low/Mod Zones | 75 | 30 | P.Facilities & Infrastructure |

Table 4 – Identify the geographic distribution and location of investments

In Program Year 2024, the City of Long Branch expended $238,479 in CDBG funds to advance its strategic goals in public services, infrastructure, and administration. Over the full 5-year Consolidated Plan period, a total of $457,589 in federal resources were made available, supporting a wide range of community development initiatives.

The geographic distribution of investments remained focused on low- and moderate-income zones, with 30% of actual allocations directed toward public facilities and infrastructure improvements in these areas. Public Services received 25% of the actual allocation, aligning precisely with the planned percentage and demonstrating the city’s commitment to maintaining essential services for vulnerable populations across Long Branch.

This balanced allocation reflects the city’s strategic approach to addressing both immediate service needs and long-term infrastructure goals. Public Services included outreach, education, and support programs that were delivered city-wide, while infrastructure investments targeted areas with the greatest need for physical improvements.

Although CDBG funds do not require formal matching, Long Branch successfully leveraged additional resources through partnerships with local nonprofits, service agencies, and municipal departments. These collaborations enhanced program delivery and extended the impact of federal investments. Publicly owned facilities were also utilized to host services and programs, maximizing the value of existing assets.

As the city concludes its 5-year Consolidated Plan, the strategic use of CDBG funds has resulted in measurable improvements in community well-being, infrastructure resilience, and service accessibility. These outcomes will inform future planning and investment strategies in the next Consolidated Plan cycle.

Leveraging

Explain how federal funds  leveraged additional resources (private, state and local funds), including a description of how matching requirements were satisfied, as well as how any publicly owned land or property located within the jurisdiction that were used to address the needs identified in the plan.

## CR-20 - Affordable Housing 91.520(b)

Evaluation of the jurisdiction's progress in providing affordable housing, including the number and types of families served, the number of extremely low-income, low-income, moderate-income, and middle-income persons served.

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of homeless households to be provided affordable housing units |  |  |
| Number of non-homeless households to be provided affordable housing units |  |  |
| Number of special-needs households to be provided affordable housing units |  |  |
| Total |  |  |

Table 11 – Number of Households

|  | One-Year Goal | Actual |
| --- | --- | --- |
| Number of households supported through rental assistance |  |  |
| Number of households supported through the production of new units |  |  |
| Number of households supported through the rehab of existing units |  |  |
| Number of households supported through the acquisition of existing units |  |  |
| Total |  |  |

Table 12 – Number of Households Supported

Discuss the difference between goals and outcomes and problems encountered in meeting these goals.

Discuss how these outcomes will impact future annual action plans.

Include the number of extremely low-income, low-income, and moderate-income persons served by each activity where information on income by family size is required to determine the eligibility of the activity.

| Number of Households Served | CDBG Actual | HOME Actual |  |
| --- | --- | --- | --- |
| Extremely Low-income | 0 | 0 |
| Low-income | 0 | 0 |
| Moderate-income | 0 | 0 |
| Total | 0 | 0 |

Table 13 – Number of Households Served

Narrative Information

## CR-25 - Homeless and Other Special Needs 91.220(d, e); 91.320(d, e); 91.520(c)

Evaluate the jurisdiction’s progress in meeting its specific objectives for reducing and ending homelessness through:

Reaching out to homeless persons (especially unsheltered persons) and assessing their individual needs

Addressing the emergency shelter and transitional housing needs of homeless persons

Helping low-income individuals and families avoid becoming homeless, especially extremely low-income individuals and families and those who are:  likely to become homeless after being discharged from publicly funded institutions and systems of care (such as health care facilities, mental health facilities, foster care and other youth facilities, and corrections programs and institutions);  and,  receiving assistance from public or private agencies that address housing, health, social services, employment, education, or youth needs

Helping homeless persons (especially chronically homeless individuals and families, families with children, veterans and their families, and unaccompanied youth) make the transition to permanent housing and independent living, including shortening the period of time that individuals and families experience homelessness, facilitating access for homeless individuals and families to affordable housing units, and preventing individuals and families who were recently homeless from becoming homeless again

## CR-30 - Public Housing 91.220(h); 91.320(j)

Actions taken to address the needs of public housing

Actions taken to encourage public housing residents to become more involved in management and participate in homeownership

Actions taken to provide assistance to troubled PHAs

## CR-35 - Other Actions 91.220(j)-(k); 91.320(i)-(j)

Actions taken to remove or ameliorate the negative effects of public policies that serve as barriers to affordable housing such as land use controls, tax policies affecting land, zoning ordinances, building codes, fees and charges, growth limitations, and policies affecting the return on residential investment. 91.220 (j); 91.320 (i)

Actions taken to address obstacles to meeting underserved needs.  91.220(k); 91.320(j)

Actions taken to reduce lead-based paint hazards. 91.220(k); 91.320(j)

Actions taken to reduce the number of poverty-level families. 91.220(k); 91.320(j)

Actions taken to develop institutional structure. 91.220(k); 91.320(j)

Actions taken to enhance coordination between public and private housing and social service agencies. 91.220(k); 91.320(j)

Identify actions taken to overcome the effects of any impediments identified in the jurisdictions analysis of impediments to fair housing choice.  91.520(a)

## CR-40 - Monitoring 91.220 and 91.230

Describe the standards and procedures used to monitor activities carried out in furtherance of the plan and used to ensure long-term compliance with requirements of the programs involved, including minority business outreach and the comprehensive planning requirements

Citizen Participation Plan 91.105(d); 91.115(d)

Describe the efforts to provide citizens with reasonable notice and an opportunity to comment on performance reports.

CR-45 - CDBG 91.520(c)

Specify the nature of, and reasons for, any changes in the jurisdiction’s program objectives and indications of how the jurisdiction would change its programs as a result of its experiences.

Does this Jurisdiction have any open Brownfields Economic Development Initiative (BEDI) grants?

[BEDI grantees]  Describe accomplishments and program outcomes during the last year.

## CR-45 - CDBG 91.520(c)

Specify the nature of, and reasons for, any changes in the jurisdiction’s program objectives and indications of how the jurisdiction would change its programs as a result of its experiences.

Does this Jurisdiction have any open Brownfields Economic Development Initiative (BEDI) grants?

[BEDI grantees]  Describe accomplishments and program outcomes during the last year.

## CR-58 – Section 3

Identify the number of individuals assisted and the types of assistance provided

| Total Labor Hours | CDBG | HOME | ESG | HOPWA | HTF |
| --- | --- | --- | --- | --- | --- |
| Total Number of Activities | 0 | 0 | 0 | 0 | 0 |
| Total Labor Hours |  |  |  |  |  |
| Total Section 3 Worker Hours |  |  |  |  |  |
| Total Targeted Section 3 Worker Hours |  |  |  |  |  |

Table 15 – Total Labor Hours

| Qualitative Efforts - Number of Activities by Program | CDBG | HOME | ESG | HOPWA | HTF |
| --- | --- | --- | --- | --- | --- |
| Outreach efforts to generate job applicants who are Public Housing Targeted Workers |  |  |  |  |  |
| Outreach efforts to generate job applicants who are Other Funding Targeted Workers. |  |  |  |  |  |
| Direct, on-the job training (including apprenticeships). |  |  |  |  |  |
| Indirect training such as arranging for, contracting for, or paying tuition for, off-site training. |  |  |  |  |  |
| Technical assistance to help Section 3 workers compete for jobs (e.g., resume assistance, coaching). |  |  |  |  |  |
| Outreach efforts to identify and secure bids from Section 3 business concerns. |  |  |  |  |  |
| Technical assistance to help Section 3 business concerns understand and bid on contracts. |  |  |  |  |  |
| Division of contracts into smaller jobs to facilitate participation by Section 3 business concerns. |  |  |  |  |  |
| Provided or connected residents with assistance in seeking employment including: drafting resumes,preparing for interviews, finding job opportunities, connecting residents to job placement services. |  |  |  |  |  |
| Held one or more job fairs. |  |  |  |  |  |
| Provided or connected residents with supportive services that can provide direct services or referrals. |  |  |  |  |  |
| Provided or connected residents with supportive services that provide one or more of the following: work readiness health screenings, interview clothing, uniforms, test fees, transportation. |  |  |  |  |  |
| Assisted residents with finding child care. |  |  |  |  |  |
| Assisted residents to apply for, or attend community college or a four year educational institution. |  |  |  |  |  |
| Assisted residents to apply for, or attend vocational/technical training. |  |  |  |  |  |
| Assisted residents to obtain financial literacy training and/or coaching. |  |  |  |  |  |
| Bonding assistance, guaranties, or other efforts to support viable bids from Section 3 business concerns. |  |  |  |  |  |
| Provided or connected residents with training on computer use or online technologies. |  |  |  |  |  |
| Promoting the use of a business registry designed to create opportunities for disadvantaged and small businesses. |  |  |  |  |  |
| Outreach, engagement, or referrals with the state one-stop system, as designed in Section 121(e)(2) of the Workforce Innovation and Opportunity Act. |  |  |  |  |  |
| Other. |  |  |  |  |  |

Table 16 – Qualitative Efforts - Number of Activities by Program

Narrative